## Slide 1
CEN3031 · SPRINT 0 · PROJECT DESIGN & PLAN
Stake.
Put something on the line.
A social accountability app that turns goals into promises your friends can see.
Productivity Masters
Ronin Mithaug · Connor Opdyke · Miguel Rosario
Notes: RONIN: Good [morning/afternoon]. We're Productivity Masters, and this is Stake, a social accountability app where you literally put something on the line for your goals. Over the next fifteen minutes we'll walk you through the problem, our solution, how we'll build it, the risks we're planning for, and exactly what we're committing to in Sprint 1.

## Slide 2
THE TEAM
Three roles, one product
Ronin Mithaug
Product Owner
Owns product vision
Prioritizes the backlog
Accepts finished stories
Presents: problem, solution, user stories
Miguel Rosario
Development Team Lead
Owns architecture
Sets up the PERN stack
Reviews pull requests
Presents: tech stack, architecture
Connor Opdyke
Scrum Master
Runs planning & standups
Keeps the Jira board current
Removes blockers
Presents: risks, backlog, Sprint 1
All three of us write code; the roles define who owns each decision.
Stake · Productivity Masters 02 / 15
Notes: RONIN: I'm Ronin, the Product Owner. I own the vision and the backlog, and I decide what gets built first. Miguel is our Development Team Lead; he owns the architecture and code quality. Connor is our Scrum Master; he runs our sprint ceremonies and keeps the Jira board honest. All three of us are developers, so the roles are about who owns each decision, not who writes code. I'll cover the product, Miguel will cover the design, and Connor will cover the plan.

## Slide 3
THE PROBLEM
Productivity apps run on willpower,
and willpower is easy to ignore.
Reminders get swiped away
A notification is a suggestion. Dismissing it costs nothing.
Nobody is watching
When you quit a streak in a private app, no one ever knows.
Failing has no cost
Skip the gym, skip the study session, and nothing happens.
Stake · Productivity Masters 03 / 15
Notes: RONIN: Here's the problem. Almost every productivity app depends on self-discipline. They send reminders, track streaks, show charts, but all of it is private and all of it is optional. If you swipe away the reminder, nothing happens. If you break your streak, nobody knows. We think that's why so many people download a habit tracker in January and stop opening it by February. The missing ingredient isn't information, it's consequences and accountability.

## Slide 4
OUR SOLUTION
How Stake works
01
Set a goal
Pick how often (daily, 3×/week) and a daily check-in deadline.
02
Stake a photo
Upload an embarrassing photo. It stays hidden and locked while the goal is active.
03
Check in
Post a timestamped photo of yourself doing it. Friends can flag fakes.
04
Miss it, it posts
Miss the deadline and your stake goes to your friends' feed. Restake and try again.
Stake · Productivity Masters 04 / 15
Notes: RONIN: Stake adds real consequences. First, you set a goal, like going to the gym three times a week, with a daily deadline. Second, before the goal starts, you upload an embarrassing photo of yourself as your stake. It follows our content guidelines, it stays hidden, and you can't delete it while the goal is active. Third, you prove you did it by checking in with a photo before the deadline. Friends see check-ins and can flag ones that look fake. Fourth, if you miss, the app automatically posts your stake to your friends' feed. Then you can upload a new stake and keep going.

## Slide 5
WHY STAKE IS DIFFERENT
Accountability you can't swipe away
 | Typical habit apps (e.g. Habitify) | Stake
Motivation | Reminders | Social pressure + a personal stake
Who sees progress | Only you | Your friends, on a feed and calendar
Cost of skipping | Nothing | Your stake photo is posted
Proof of completion | Tap a checkbox | Timestamped photo, flaggable by friends
For people who want to be more productive, Stake makes progress visible to friends and puts a personal stake on every goal.
Stake · Productivity Masters 05 / 15
Notes: RONIN: So how does this answer the challenge statement? [Tie to the exact wording of your challenge statement here.] Compare Stake to a typical habit app like Habitify. Those apps motivate you with reminders; we motivate you with social pressure and a personal stake. In those apps only you see your progress; in Stake your friends see it on your feed and your calendar. Skipping costs you nothing there; here your stake photo gets posted. And instead of tapping a checkbox, you prove it with a timestamped photo your friends can flag. That's our vision: accountability you can't swipe away.

## Slide 6
USER STORIES
Built around four real users
YOUNG ADULT
“I want accountability for going to the gym, so that I can be healthier.”
Done when: a missed check-in posts my stake to friends.
ATHLETE
“I want to see my progress and my friends' milestones, so I keep up with my goals.”
Done when: the feed shows goals met and photos of goals failed.
STUDENT
“I want to stay ahead of my courses, so I stop cramming at the last minute.”
Done when: I can register, log in, log out and set a goal.
ADMIN
“I want the platform to be safe, so that users don't break the rules.”
Done when: I can view reports and remove images or ban users.
Stake · Productivity Masters 06 / 15
Notes: RONIN: Our backlog grows out of four user stories. A young adult wants accountability at the gym; for them, done means a missed check-in actually posts their stake. An athlete wants to see their own progress and their friends' milestones, so the feed has to show goals met and failed. A student wants to stop procrastinating, and the first thing they need is to register, log in, and set a goal. And an admin wants the platform to be safe, so they need to review reports, remove images, and ban users who break the rules. We mapped these into three releases, which Connor will show in the backlog. Now Miguel will walk through how we'll build it.

## Slide 7
LANGUAGES, FRAMEWORKS & TOOLS
The PERN stack, end to end in JavaScript
Frontend
React · HTML · CSS
Reusable components for photo cards, goal calendars and the feed.
Backend
Node.js · Express
One language across the stack; one API enforces every auth and deadline rule.
Database
PostgreSQL · SQL
Relational data with transactions, so a stake is released exactly once.
Team tools
GitHub · Jira
Branches and PR reviews in GitHub; backlog, sprints and estimates in Jira.
Planned libraries
React Router · pg (node-postgres) · bcrypt · Multer · node-cron · Jest
Stake · Productivity Masters 07 / 15
Notes: MIGUEL: Thanks, Ronin. We're building on the PERN stack. React on the frontend, because Stake is full of repeated pieces like photo cards, calendars and feed items, and components let us build those once. Node and Express on the backend, which means the whole team works in one language, JavaScript, and every client goes through one API that enforces authorization and deadline rules. PostgreSQL for the database, because our data is relational: users, goals, check-ins, friendships. Its transactions matter a lot for us, because releasing a stake has to happen exactly once. We coordinate with GitHub for version control and pull request reviews, and Jira for our backlog and sprints. Libraries we're planning on include React Router, node-postgres, bcrypt for password hashing, Multer for photo uploads, node-cron for our deadline job, and Jest for testing.

## Slide 8
ARCHITECTURAL DESIGN
System architecture model
Presentation
React in the browser: profile, goal forms, calendar, feed, moderation
↓ HTTPS · JSON and photo uploads ↓
One Node.js / Express backend (modular monolith)
Request handling
Routes · sessions · authorization · input validation
Accounts
Login, profiles, roles
Goals & check-ins
Schedules, stake lifecycle
Social & moderation
Friends, feed, reports
Deadline job
Releases missed stakes
Data access
Repositories (SQL, transactions) + photo storage adapter
PostgreSQL
Users, goals, windows, check-ins, reports
Private photo storage
Server-controlled access only
Layered client-server
Separation of concerns. The UI can change without touching deadline rules or SQL.
One source of truth. Every browser hits the same rules and the same database.
Right-sized. One backend is simpler for three people to build, test and deploy than microservices.
Stake · Productivity Masters 08 / 15
Notes: MIGUEL: For architecture we chose a layered client-server pattern. At the top, React runs in each user's browser and talks to our backend over HTTPS. The backend is a single Node and Express application, what's called a modular monolith. Requests come into a handling layer that checks sessions, authorization and input. Then they go to one of our modules: accounts, goals and check-ins, or social and moderation. There's also an internal deadline job, which runs on a timer instead of a browser request. All modules go through a data access layer to reach PostgreSQL and private photo storage. Why this design? The layers separate concerns, every client shares one set of rules and one database, and one backend is the right size for a three-person team. We don't need microservices here.

## Slide 9
KEY DESIGN DECISION
What happens at the deadline
Timer fires
The internal job wakes up. No user request needed.
Find due windows
Goal windows whose cutoff has passed, stored in UTC.
Recheck evidence
Count committed check-ins against the required number.
Met
Day marked complete on the calendar.
Missed
Stake released + feed post in one transaction.
Reliability built in: one release per window (unique constraint) · check-ins and deadline checks serialized per window · due windows rechecked after a restart
Stake · Productivity Masters 09 / 15
Notes: MIGUEL: The riskiest part of Stake is the moment a deadline passes, so we designed it carefully. An internal scheduled job wakes up on a timer. It finds every goal window whose cutoff has passed; all cutoffs are stored in UTC along with the goal's time zone. It rechecks the committed check-ins against how many the goal requires. If the goal was met, that day is marked complete on the calendar. If it was missed, the stake is released and the feed post is created in a single database transaction, and a unique constraint guarantees a window can only release once. If the server restarts, it rechecks due windows, so nothing gets skipped. Connor will now cover how we manage risk and plan the work.

## Slide 10
RISK MANAGEMENT PLAN
What could go wrong, and our plan for it
Risk | Type | Probability | Effect | Strategy
Inappropriate stake photo uploaded | Business | High | Serious | Admins review stakes before goals start; users report; admins remove and ban.
Fake check-in photo | Product | High | Tolerable | Check-ins appear on friends' feed, where they can be flagged; admins verify or deny.
Stake released by mistake (time zones) | Product | Moderate | Serious | Store all deadlines in UTC; write tests for time-zone and midnight edge cases.
Private stake photo leaks early | Product | Low | Serious | Private storage; server checks authorization on every photo request.
Scope too big for 3 people | Project | Moderate | Tolerable | Ship Release 1 first; PO guards the backlog; re-estimate each sprint.
Stake · Productivity Masters 10 / 15
Notes: CONNOR: Thanks, Miguel. Here's our risk management plan. The biggest business risk is someone uploading an inappropriate stake photo. It's likely, and serious, so admins review stakes before goals start, users can report content, and admins can remove it and ban users. Fake check-in photos are also likely but tolerable; friends see check-ins on the feed and can flag them for an admin. A stake released by mistake because of a time-zone bug is moderate probability but serious, so we store every deadline in UTC and test the edge cases. A stake photo leaking early is low probability but serious, so photos live in private storage behind authorization checks. And the project risk is scope: three people, so we ship Release 1 first and re-estimate every sprint.

## Slide 11
PRODUCT BACKLOG
Estimated with planning poker
Release 1 → Sprint 1
ID | Backlog item | Points
PBI-1 | Register, log in, log out | 5
PBI-2 | Create a goal with frequency + deadline | 5
PBI-3 | Upload a private stake photo | 8
PBI-4 | Submit a timestamped check-in photo | 5
PBI-5 | Send and accept friend requests | 5
PBI-6 | Feed of friends' check-ins | 8
 | Total | 36
Release 2 → Sprint 2
ID | Backlog item | Points
PBI-7 | Auto-release stake on a missed deadline | 13
PBI-8 | Show released stakes in the feed | 3
PBI-9 | Report a photo | 3
PBI-10 | Admin review: remove photo, ban user | 5
PBI-11 | Deadline reminders | 5
PBI-12 | Goal progress calendar on profile | 8
 | Total | 37
How we voted: Fibonacci cards (1, 2, 3, 5, 8, 13), everyone reveals at once, highest and lowest explain, then re-vote until we agree.
Stake · Productivity Masters 11 / 15
Notes: CONNOR: This is our product backlog, estimated with planning poker. Each of us voted with Fibonacci cards at the same time. When votes were far apart, the highest and lowest voters explained their thinking, and we re-voted until we agreed. For example, auto-releasing a stake came in at 13, our biggest item, because it involves the scheduler, time zones and a transaction. Something like reporting a photo is a 3. Release 1 is the core loop: accounts, goals, stakes, check-ins, friends and the feed, 36 points. Release 2 adds the consequences and safety: auto-release, reporting, admin review, reminders and the calendar, 37 points. That's 73 points total. [Update points to match your team's actual votes.]

## Slide 12
SPRINT 1 BACKLOG
36 points, 64 planned hours
Item | Tasks | Owner | Hours
Setup | Repo, PERN scaffold, database schema, dev environment | Miguel | 6
PBI-1 Auth | Sign-up/login API, bcrypt hashing, sessions, login UI | Connor | 10
PBI-2 Goals | Goals table + API, create-goal form | Ronin | 8
PBI-3 Stake | Multer upload, private storage, file validation | Miguel | 12
PBI-4 Check-in | Check-in API tied to goal window, upload UI | Ronin | 8
PBI-5 Friends | Request/accept API, friends list UI | Connor | 8
PBI-6 Feed | Paginated feed query, feed page | Miguel | 12
 | Total planned |  | 64
Sprint goal: a user can sign up, create a goal, stake a photo, check in, and see friends' check-ins.
Stake · Productivity Masters 12 / 15
Notes: CONNOR: Here's Sprint 1 broken into tasks. We start with six hours of setup: the repo, the PERN scaffold and our database schema. Then the six Release 1 items, split between the three of us: Connor on auth and friends, Ronin on goals and check-ins, Miguel on setup, stake upload and the feed. That adds up to 64 planned hours. Our sprint goal is simple: by the end of Sprint 1, a user can sign up, create a goal, stake a photo, check in, and see their friends' check-ins. [Confirm owners and hours with the team.]

## Slide 13
VELOCITY & CAPACITY
Sprint 1 fits inside what we can do
VELOCITY
36.5
points per sprint
73 total PBI points ÷ 2 sprints
CAPACITY
72
hours per sprint
3 members × 8 hrs/week × 3 weeks
COMMITTED
36
points · 64 hours
Matches velocity, with an 8-hour buffer for bugs and review
Stake · Productivity Masters 13 / 15
Notes: CONNOR: So does Sprint 1 fit? Velocity is how much work we need to do per sprint: 73 total backlog points divided by two sprints gives 36.5 points per sprint. Capacity is how much work we can actually do: three members, times eight hours a week, times three weeks, is 72 hours. We're committing 36 points, which matches our velocity, and 64 planned hours, which leaves an eight-hour buffer for bugs, code review and surprises.

## Slide 14
ISSUES & NEXT STEPS
Where we stand and what comes next
Open issues
Photo storage provider not yet chosen
Grace period and late-upload rules not agreed
Admin workload for reviewing every stake
Estimates are first-pass; re-vote after Sprint 1
Next steps
Finalize Sprint 1 tasks in Jira
Week 1: scaffold repo and database schema
Sprint 1 demo: the core goal loop
Sprint 2: auto-release, reports, admin review
Later: goal reset, account management, history
Stake · Productivity Masters 14 / 15
Notes: CONNOR: To wrap up, a few open issues. We haven't picked a photo storage provider yet. We still need to agree on grace periods and late uploads. We need to watch how much work reviewing every stake puts on admins. And our estimates are first-pass, so we'll re-vote after Sprint 1 using real data. Next steps: finalize the Sprint 1 tasks in Jira, scaffold the repo and schema in week one, and demo the core goal loop at the end of Sprint 1. Sprint 2 brings auto-release, reporting and admin review, and after that, goal resets, account management and progress history.

## Slide 15
Put something
on the line.
Thank you. Questions?
Ronin Mithaug · Connor Opdyke · Miguel Rosario · github.com/miguelrosari0/SWEproj2026
Notes: ALL (Ronin leads): That's Stake. Most apps ask you to hold yourself accountable; Stake makes your friends part of it. Thank you, and we're happy to take any questions.